## Slide 1: Request for proposal
Big data collecting and analytics platform for strategic product development

## Slide 2: Agenda
About us
Project objective and scope
Requirements
Milestones
WBS
Bidding information

## Slide 3: About us
RUSSIAN
FEDERATION
UKRAINE
TURKEY
SWITZERLAND
SLOVENIA
SLOVAKIA
SERBIA
ROMANIA
PORTUGAL
POLAND
MOLDOVA
MALTA
MACEDONIA
LITHUANIA
LATVIA
LATGALE
KOSOVO
IRELAND
GEORGIA
ICELAND
HUNGARY
GREECE
MONACO
FINLAND
ESTONIA
DENMARK
CZECH
REPUBLIC
CYPRUS
CROATIA
BELGIUM
LUXEMBURG
BULGARIA
BELARUS
BOSNIA
AND
HERZEGOVINA
LICHTENSTEIN
MONTENEGRO
ANDORRA
ALBANIA
AUSTRIA
SPAIN
SWEDEN
NORWAY
NETHERLANDS
ITALY
GERMANY
FRANCE
UNITED
KINGDOM
SAN MARINO
We build innovative household robots for cleaning. Our robots have high-quality sensors and the most advanced software in the market in an smart design.
We collaborate with the most important Italian institutes of robotics.
We are based in Pisa. Our company counts 200+ employees.
We sell our robots all over Italy and currently we are shipping all over Europe.

## Slide 4: Project objective and scope
Our objective is to improve our products development process.
To this aim we want a platform able to integrate and manage huge quantity of data coming from different sources.
Data sources are: R&D department system, social networks, web site and mobile application.

## Slide 5: Project objective and scope
Project tasks
Development of a database for big data.
Development of a data collecting and merging tool.
Development of an analytics system.
Development of a dashboard.
Integration with our system.

## Slide 6: Requirements
    The system should be compatible with Microsoft Azure.
    The dashboard should be integrated in our web-application.
Integration with our system

## Slide 7: Requirements
    The system should reduce the risk of data losses.
Fault tolerance

## Slide 8: Requirements
    The dashboard should be user-friendly.
    The dashboard should be easy to navigate.
Usability(1)

## Slide 9: Requirements
    The data should be visualized for type of product and date.
    The customers reviews should be searchable by keywords.
    The R&D datasheets should be searchable by keywords.
Usability(2)

## Slide 10: Requirements
    The system should show tag clouds and histograms of customer review’s keywords.
    The system should forecast an approval rating for each product.
    The system should show reports on past selling trends and forecast selling trends.
Analytics(1)

## Slide 11: Requirements
    The system should list R&D reports related with customer review’s keywords.
    The system should identify the most active and relevant customers on our social profiles.
Analytics(2)

## Slide 12: Requirements
    The system should be compliant with the GDPR.
Legal

## Slide 13: Milestones
Project start 22 Jun.
Final test document
Architecture 6 Jul.
Test and deploy 14 Dec.
Prototype 16 Nov.
1st Demo 20 Jul.
2nd Demo 17 Aug.
3rd Demo 14 Sep.
4th Demo 12 Oct.
System design document
Design 29 Jun.
System architecture document
Mokup
Dashboard 13 Jul.
User manual
Mokup
Final dashboard 13 Jul.
Implemented features and tests
Implemented features and tests
Implemented features and tests
Implemented features and tests

## Slide 14: WBS
SPD Software
Storage module
Analytics module
Data collecting and merging tool
Dashboard
Integration

## Slide 15: Bidding information
Proposals should be submitted until 4:30 pm May 30, 2020. Any proposal received after the end date will be rejected.
Contract terms and condition will be negotiated with the winning bidder for this RFP.
Contractual terms and condition will be reviewed by our legal department.
General

## Slide 16: Bidding information
Preliminary design of the solution
Detailed description of how it will be developed, what technologies will be used
Description of costs.
If the used IaaS is different from Microsoft Azure, bidders should provide a description of the features of that IaaS.
Documents to submit

## Slide 17: Bidding information
Detailed pricing is required for each of the following items:
  Project initiation and planning.
  Software development.
  Software testing.
  Software deployment.
Detailed pricing and amount of additional infrastructure resources needed is also required.
The budget for this project is 250.000 EUR.
Costs

## Slide 18: Bidding information
Overall proposal suitability: the proposed solution should meet the scope of this project.
Integration and performance: how well the bidders’ proposed system is integrated with our existing system.
Value and cost: bidders will be evaluated on the cost of the proposed solution based on the work to be performed.
Evaluation criteria